## Work Breakdown Structure
Sprint - 1
SN | TASK ASSIGNED | PERSON RESPONSIBLE | START DATE | END DATE | STATUS
WEEK 1
1 | UI/UX Design (Figma Prototyping) | KN | 2026-03-22 | 2026-03-29 | DONE
2 | GitHub Repository & Branching Setup | SR | 2026-03-27 | 2026-04-04 | DONE
3 | Setup Live Hosting & Initial Deployment | SD | 2026-03-27 | 2026-04-02 | DONE
4 | Research on Risks & Project Planning | Team | 2026-03-22 | 2026-03-28 | DONE
WEEK 2
1 | Voter Login Portal & Landing Page | KN | 2026-03-22 | 2026-04-03 | DONE
2 | Admin Login & Security Implementation | SR | 2026-03-22 | 2026-04-07 | DONE
3 | Voter Session & Access Restrictions | KN | 2026-03-22 | 2026-04-07 | DONE
4 | Admin Activity Logging | SR | 2026-03-22 | 2026-04-02 | DONE
WEEK 3
1 | Voter Profile & Active Polls Display | RK | 2026-03-22 | 2026-04-09 | DONE
2 | Candidate Listing per Pool | RK | 2026-03-22 | 2026-04-09 | DONE
3 | Ballot Selection (Voting Interface) | RK | 2026-03-22 | 2026-04-09 | DONE
4 | Vote Confirmation System | RK | 2026-03-22 | 2026-04-10 | DONE
5 | Secondary Verification Modal | KN | 2026-03-22 | 2026-04-08 | DONE
WEEK 4
1 | NID Integration & Validation | KN | 2026-03-22 | 2026-04-13 | DONE
2 | Constituency Auto-Sync Engine | RK | 2026-03-22 | 2026-04-11 | DONE
3 | Create & Configure Election Pool | SR | 2026-03-22 | 2026-04-13 | DONE
4 | View & Filter Election Pool | SR | 2026-03-22 | 2026-04-15 | DONE
5 | Admin Profile Management | SR | 2026-03-22 | 2026-04-15 | DONE
6 | Live Result Dashboard | RK | 2026-03-22 | 2026-04-09 | DONE
7 | Final Deployment & Testing | SD | 2026-04-05 | 2026-04-15 | DONE
Sprint - 2
SN | TASK ASSIGNED | PERSON RESPONSIBLE | START DATE | END DATE | STATUS
WEEK 1
1 | Implement wazuh for Monitoring | SD | 2026-04-26 | 2026-05-01 | DONE
2 | Missing Search & Filter Functionality | KN | 2026-04-26 | 2026-05-01 | DONE
3 | Enforce SSL/TLS & Secure Headers | KD | 2026-04-26 | 2026-04-29 | DONE
WEEK 2
1 | Strict Single-Session & Timeout (Voter) | KN | 2026-04-26 | 2026-05-02 | DONE
2 | Simplified Navigation & Interactive Guide | RK | 2026-04-26 | 2026-05-02 | DONE
3 | UI Mismatch - Result Portal | RK | 2026-04-26 | 2026-05-02 | DONE
4 | Admin Voter Deletion Crash - Foreign Key | SR | 2026-04-26 | 2026-05-03 | DONE
WEEK 3
1 | Login Captcha & Email OTP (admin) | SR | 2026-04-26 | 2026-05-05 | DONE
2 | Web Vulnerabilities Mitigations | SR | 2026-04-26 | 2026-05-06 | DONE
3 | Voter Session & Access Restrictions | KN | 2026-04-26 | 2026-05-05 | DONE
4 | Security Implementation: VPN & Proxy | SR | 2026-04-26 | 2026-05-07 | DONE
5 | Voter Profile- Navigation contents not visible | RK | 2026-04-26 | 2026-05-10 | DONE
6 | Voting Flow- Secondary verification bypassed | RK | 2026-04-26 | 2026-05-10 | DONE
7 | Information Disclosure | SR | 2026-04-26 | 2026-05-09 | DONE
WEEK 4
1 | Core Logic Flaw | SR | 2026-05-06 | 2026-04-13 | DONE
2 | Isolate Sensitive Files & Config | SR | 2026-04-26 | 2026-04-11 | DONE
3 | Admin Candidate Deletion Crash- Foreign Key | SR | 2026-05-06 | 2026-04-14 | DONE
4 | UI Mismatch - Admin Navigation Duplication | KN | 2026-05-06 | 2026-04-16 | DONE
5 | Voter UI - Voted pools remain active after vote | KN | 2026-05-06 | 2026-05-13 | DONE
6 | UI Mismatch - Voting Ballot and summary | RK | 2026-05-06 | 2026-05-11 | DONE
7 | UI Mismatch - Admin Dashboard layout | KN | 2026-05-06 | 2026-04-16 | DONE
8 | Authentication Bypass- Voter logins succeeds without OTP validation | SR | 2026-05-06 | 2026-04-17 | DONE

## Risk Register
Risk Register
RISK DESCRIPTION | IMPACT DESCRIPTION | IMPACT LEVEL | PROBABILITY LEVEL | PRIORITY LEVEL | MITIGATION NOTES | OWNER
Give a brief summary of the risk. | What will happen if the risk is not mitigated or eliminated? | Rate 1 (LOW) to 5 (HIGH) | Rate 1 (LOW) to 5 (HIGH) | (IMPACT X PROBABILITY) Address the highest first. | What can be done to lower or eliminate the impact or probability? | Who's responsible? | Level
1
2
3
4
5

## Attendance
Sprint 1: Client Meeting attendance
NAME | March 22nd 2026 | March 29th 2026 | April 5th 2026 | April 12th 2026 | Index
Aadarsha K.C. (PM) | P | P | P | P | P = Present
Suwan Dhital (BA) | P | AR | P | P | A = Absent
Subrat Regmi | P | P | P | P | AR = Absent (Apology received)
Kriteeka Neupane | AR | P | P | P
Riyana Khand | P | P | P | P
Sprint 2: Client Metting Attendance
NAME | April 26th 2026 | May 3rd 2026 | May 10th 2026 | May 17th 2026
Aadarsha K.C. (PM) | P | P | P | P
Suwan Dhital (BA) | P | P | AR | P
Subrat Regmi | P | P | P | P
Kriteeka Neupane | P | P | P | P
Riyana Khand | AR | P | P | P

## Backlog division
Product Backlog
Task ID | Summary | Role | Sprint | SP | Start | End | Labels
OVMS-53 | UI/UX design | KN | 1 | 2 | 24th March | 29th March | UI/UX & Figma Designs | Name | SP
OVMS-37 | Admin Dashboard & Metrics | SR | 1 | 3 | 22th March | 30th March | Admin Dashboard & Analystics | Subrat Regmi | 16
OVMS-38 | Admin Activity Logging | SR | 1 | 2 | 22th March | 2th April | Admin Dashboard & Analystics | Kriteeka Neupane | 14
OVMS-61 | Technical - Setup Live Hosting, Database & Deployment | SD | 1 | 2 | 27th March | 11th April | Technical setup & Manual Deployment | Riyana Khand | 12
OVMS-23 | Voter Login Portal and Landing Home Page | KN | 1 | 3 | 22th March | 3rd April | Voter Authentication & restriction | Suwan Dhital | 2
OVMS-59 | Technical - GitHub Repository & Branching Strategy Setup | SR | 1 | 1 | 27th March | 4th April | Technical setup & Manual Deployment
OVMS-25 | Voter Profile & Active Pools Display | RK | 1 | 3 | 22th March | 9th April | Voter Dashboard & Navigation
OVMS-34 | Admin login & Security | SR | 1 | 3 | 22th March | 7th April | Admin authentication & Profile
OVMS-39 | Voter Verification Search | KN | 1 | 2 | 22th March | 5th April | Voter & Candidate Management
OVMS-24 | Voter Session & Access Restrictions | KN |  | 2 | 22th March | 7th April | Voter Authentication & restriction
OVMS-32 | Final Submission & Auto-Logout | KN | 1 | 2 | 22th March | 7th April | The Voting Flow
OVMS-29 | Secondary Verification Modal | KN | 1 | 2 | 22th March | 8th April | The Voting Flow
OVMS-26 | Candidate Listing per Pool | RK | 1 | 1 | 22th March | 9th April | Voter Dashboard & Navigation
OVMS-46 | Live Result Dashboard | RK | 1 | 2 | 22th March | 9th April | Public Result Portal
OVMS-30 | Ballot Selection (Information Grid) | RK | 1 | 2 | 22th March | 9th April | The Voting Flow
OVMS-40 | Add & Edit Candidate | SR | 1 | 1 | 22th March | 10th April | Voter & Candidate Management
OVMS-31 | Vote Confirmation | RK | 1 | 1 | 22th March | 10th April | The Voting Flow
OVMS-57 | Technical - Constituency Auto-Sync Engine | RK | 1 | 3 | 22th March | 11th April | System Integration & Database Architecture
OVMS-56 | Technical - NID Integration & Validation | KN | 1 | 3 | 22th March | 13th April | System Integration & Database Architecture
OVMS-43 | Create & Configure New Pool | SR | 1 | 2 | 22th March | 13th April | Election Pool Management
OVMS-35 | Admin Profile Management | SR | 1 | 3 | 22th March | 15th April | Admin authentication & Profile
OVMS-42 | View & Filter Elections pool | SR | 1 | 1 | 22th March | 15th April | Election Pool Management
Product Backlog
Task ID | Summary | Role | Sprint | SP | Start | End | Labels
OVMS-64 | Strict Single-Session & Timeout (Voter) | KN | 2 | 4 | 26th April | 2nd May | Advanced Authentication & Strict Session Control
OVMS-63 | Login CAPTCHA & Email OTP (Admin) | SR | 2 | 3 | 26th April | 5th May | Advanced Authentication & Strict Session Control
OVMS-66 | Web Vulnerability Mitigations | SR | 2 | 3 | 26th April | 6th May | Security, Compliance & Vulnerability Management
OVMS-65 | Simplified Navigation & Interactive Guide | RK | 2 | 2 | 26th April | 2nd May | Accessibility & UI/UX Improvements
OVMS-85 | Security Implementation - VPN & Proxy | SD | 2 | 2 | 26th April | 7th May | Security, Compliance & Vulnerability Management | Name | SP
OVMS-67 | Isolate Sensitive Files & Configs | SR | 2 | 2 | 26th April | 11th May | Security, Compliance & Vulnerability Management | Subrat Regmi | 21
OVMS-75 | UI Mismatch - Result Portal | RK | 2 | 1 | 26th April | 2nd May | Accessibility & UI/UX Improvements | Kriteeka Neupane | 16
OVMS-68 | Enforce SSL/TLS & Secure Headers | SD | 2 | 3 | 26th April | 29th April | Security, Compliance & Vulnerability Management | Riyana Khand | 14
OVMS-76 | Implement Wazuh for Monitoring | SD | 2 | 4 | 26th April | 1st May | Security, Compliance & Vulnerability Management | Suwan Dhital | 9
BUG-Tickets
OVMS-73 | Admin Voter Deletion Crash - Foreign Key Constraint (candidates) | SR | 2 | 2 | 26th April | 3rd May
OVMS-72 | Admin Candidate Deletion Crash- Foreign Key Constraint (pool_candidates) | SR | 2 | 3 | 6th May | 14th May
OVMS-74 | Missing Search & Filter Functionality Across All Data Tables | KN | 2 | 3 | 26th April | 1st May | Accessibility & UI/UX Improvements
OVMS-77 | UI Mismatch - Admin Navigation Duplication (Left Pane & Top Bar) | KN | 2 | 3 | 6th May | 16th May
OVMS-78 | Voter UI - Voted pools remain active after casting a ballot | KN | 2 | 3 | 6th May | 13th May
OVMS-79 | Voter Profile - Navigation contents are not visible | RK | 2 | 3 | 6th May | 10th May | Accessibility & UI/UX Improvements
OVMS-80 | Voting Flow - Secondary verification is bypassed on "Vote Now | RK | 2 | 2 | 6th May | 8th May | Advanced Authentication & Strict Session Control
OVMS-81 | UI Mismatch - Voting ballot and summary screens do not match wireframes | RK | 2 | 2 | 6th May | 11th May | Accessibility & UI/UX Improvements
OVMS-83 | UI Mismatch - Admin Dashboard layout is disproportionately large and cluttered | KN | 2 | 3 | 6th May | 16th May | Accessibility & UI/UX Improvements
OVMS-84 | Authentication Bypass - Voter login succeeds without OTP validation | SR | 2 | 2 | 6th May | 17th May | Advanced Authentication & Strict Session Control
OVMS-86 | Information Disclosure - Sensitive configuration files exposed to public web traffic | SR | 2 | 2 | 6th May | 9th May | Security, Compliance & Vulnerability Management
OVMS-87 | Core Logic Flaw - Proportional Ballot shows Individual Candidates instead of Political Parties | SR | 2 | 4 | 6th May | 14th May
| Name | Total-SP
| Subrat Regmi | 37
| Kriteeka Neupane | 30
| Riyana Khand | 26
| Suwan Dhital | 11

## Product Sprint Backlog
Requirement | Priority | User stories | Acceptance Criteria | Points/Time Estimate | Status
SYS-UX-1.0 (OVMS-53) | Medium | As a Business Analyst/Designer, I want to create complete Figma mockups so that developers have clear wireframes for the voting interface. | High-fidelity mockups for voter dashboard, admin panel, and verification modals are completed and approved. | 2 | DONE
PM-F-1.0 (OVMS-42) | High | As an admin, I want to view and filter election pools so that I can monitor their status. | Table shows pool name, type, and status; filterable by constituency or election type; status (upcoming/active/closed) visually distinguishable. | 1 | DONE
AM-F-2.0 (OVMS-35) | Low | As an admin, I want to manage my profile and change my password so that my account remains secure. | Can view/edit name and email; password change requires current password and meets minimum strength criteria. | 3 | DONE
PM-F-2.0 (OVMS-43) | High | As an admin, I want to create and configure new election pools so that voters have active elections to participate in. | Form accepts pool name, type, and constituency; validates end date is later than start date; links pool to database correctly. | 2 | DONE
SYS-F-2.0 (OVMS-57) | High | As a system, I need to auto-synchronise voter constituencies based on their NID permanent address so that manual assignment errors are avoided. | Background engine successfully maps voter NID address to the correct constituency and active election pool automatically. | 3 | DONE
SYS-ENV-1.0 (OVMS-61) | High | As a developer, I want to set up live hosting and database deployment so that the application is accessible online. | Azure VM configured with Linux/Ubuntu; web server running; database securely connected; application loads via URL. | 2 | DONE
VT-F-2.0 (OVMS-31) | High | As a voter, I want to view a vote confirmation screen before final submission so that I don't cast an erroneous vote. | Screen displays selected candidate and party prominently; includes warning that vote is final; 'Confirm Vote' button is functional. | 1 | DONE
AM-F-1.0 (OVMS-37) | Medium | As an admin, I want a dashboard with real-time metrics so that I can monitor total voters, candidates, and votes cast. | Statistics fetched dynamically without page reload; data presented in labelled summary cards. | 3 | DONE
SYS-DB-1.0 (OVMS-2) | High | As a developer, I want to set up the 13-table database architecture so that data referential integrity is maintained. | MySQL database implemented with foreign keys and unique constraints (e.g., voter_hash + pool_id). | 1 | DONE
AUTH-F-1.0 (OVMS-23) | High | As a voter, I want to log in using my NID and date of birth so that I can securely access the voting portal. | Accepts NID/DOB; enforces max 5 failed attempts before temporary block; transmits over HTTPS. | 3 | DONE
VT-F-3.0 (OVMS-32) | High | As a voter, I want to submit my vote and receive a receipt code so that I know my ballot was successfully recorded. | Inserts row into votes table with voter_hash; displays unique receipt code and 5-second countdown to auto-logout. | 2 | DONE
VM-F-2.0 (OVMS-24) | High | As a system, I want to enforce session and access restrictions so that voters cannot vote multiple times or after a pool closes. | Server-side validation prevents access after voting in all pools; sessions auto-terminate after 10 minutes of inactivity (AUTH-F-1.3). | 2 | DONE
CM-F-1.0 (OVMS-26) | High | As an admin, I want to view candidate listings per pool so that I can verify who is running in which constituency. | Displays candidate list filterable by district and constituency; displays name, party, and nomination status. | 1 | DONE
VT-F-1.0 (OVMS-29) | High | As a voter, I want to verify my identity via a modal using my citizenship number and CAPTCHA so that the ballot is secure. | Modal requires citizenship number and CAPTCHA; validates against citizens table; max 3 attempts allowed. | 3 | DONE
VM-F-1.4 (OVMS-30) | High | As a voter, I want to select a candidate from an information grid so that I can make my voting choice easily. | Grid displays candidate photo, name, party, and symbol; 'Vote Now' button is available for unvoted pools. | 2 | DONE
AUTH-F-2.0 (OVMS-34) | High | As an admin, I want to log in using my email, password, and an OTP (2FA) so that the backend is protected. | Requires email/password; sends OTP to registered email; locks after 5 failed attempts; sessions expire after 30 mins. | 3 | DONE
AM-F-1.1 (OVMS-38) | Medium | As an admin, I want the system to log administrative actions so that there is an audit trail for security. | System records admin actions, timestamps, and IP addresses persistently in the database. | 2 | DONE
SYS-DEV-1.0 (OVMS-59) | High | As a developer, I want to set up the GitHub repository and branching strategy so that the team can collaborate on code. | Repository initialized; main/dev branches created; config files with credentials excluded from version control. | 1 | DONE
VM-F-1.0 (OVMS-25) | High | As a voter, I want to view my profile and active pools so that I know which elections I am eligible for. | Automatically detects and displays constituency; lists only active pools associated with the voter; hides voted pools. | 1 | DONE
UM-F-1.0 (OVMS-39) | Medium | As an admin, I want to search for voters by NID or name so that I can verify voter records. | Accessible only to admins; supports partial NID/name entry; displays linked citizen record details on selection. | 2 | DONE
CM-F-2.0 (OVMS-40) | High | As an admin, I want to add and edit candidates using their NID so that ballot data is accurate. | Auto-fetches citizen details via NID in real-time; auto-populates party symbol; allows editing of active/inactive status. | 1 | DONE
RM-F-1.0 (OVMS-46) | High | As a public user, I want to view a live results dashboard so that I can track election outcomes transparently. | Publicly accessible without login; filterable by area/pool; shows total votes per candidate updating in near-real time. | 2 | DONE
SYS-F-1.0 (OVMS-56) | High | As a system, I need NID integration and validation so that invalid NID formats do not query the database. | System validates NID format prior to database query; NID lookups execute in real time against the registry. | 3 | DONE
Requirement | Priority | User stories | Acceptance Criteria | Points/Time Estimate | Status
OVMS-64: Strict Single-Session & Timeout (Voter) | High | As a voter, I want my session to expire after inactivity or a new login so my account remains secure. | Clear previous sessions on new login,Implement 10-minute inactivity timeout, Server-side token destruction. | 2 | DONE
OVMS-63: Login CAPTCHA & Email OTP (Admin) | High | As an admin, I want a multi-factor login process to protect sensitive system controls. | Integrate CAPTCHA on login, Generate and send 6-digit email OTP, Lock account after 3 failed attempts. | 3 | DONE
OVMS-66: Web Vulnerability Mitigations | High | As a security engineer, I want the app hardened against common attacks to prevent data breaches. | Implement parameterized queries (SQLi), Sanitize all inputs (XSS), Implement CSRF tokens. | 2 | DONE
OVMS-65: Simplified Navigation & Interactive Guide | Medium | As a user, I want a clean interface and a guide so I can navigate the voting process easily. | Streamline menus per wireframe, Add a dismissible "How to Vote" guide, Add breadcrumb navigation. | 2 | DONE
OVMS-85: Security Implementation - VPN & Proxy | High | As an admin, I want the portal accessible only via VPN to prevent public exposure. | Configure WireGuard/OpenVPN, Implement IP whitelisting at proxy level, Return 403 for non-VPN traffic. | 2 | DONE
OVMS-67: Isolate Sensitive Files & Configs | High | As a developer, I want to hide internal files so attackers cannot see our credentials. | Move .env outside web root, Disable directory listing, Restrict access to /vendor and /logs. | 2 | DONE
OVMS-75: UI Mismatch - Result Portal | Medium | As a stakeholder, I want the results portal to match wireframes for professional presentation. | Update CSS to match Wireframe designs, Align charts and candidate cards, Ensure responsive layout. | 1 | DONE
OVMS-68: Enforce SSL/TLS & Secure Headers | High | As a system admin, I want all traffic encrypted to prevent man-in-the-middle attacks. | Force HTTP to HTTPS redirect, Enforce TLS 1.2/1.3 only, Implement HSTS and CSP headers. | 3 | DONE
OVMS-76: Implement Wazuh for Monitoring | Medium | As a security officer, I want real-time monitoring to detect and respond to threats. | Deploy Wazuh manager/agent, Configure file integrity monitoring, Set up automated security alerts. | 4 | DONE

## Test case
TC#ID | Req#ID | Scenario | Testcase Title | steps | Test Data | Expected Results | Actual result | Status | Comments
TC-01 | AUTH-F-1.0 (OVMS-23) | Voter Login — Valid Credentials | Verify voter can log in with correct NID and date of birth | 1. Navigate to https://votingsystme.tech/ovms/voter/login 2. Enter valid NID in the NID field 3. Enter correct date of birth 4. Click 'Login' | NID: 1234567890123 Voter ID: VTR-2081-000001 Password: pwd1234567890123 | Voter is redirected to the Voter Dashboard. Session is created. Active pools for the voter's constituency are visible. | Same as expected | PASS | worked fine
TC-02 | AUTH-F-1.0 (OVMS-23) | Voter Login — Invalid NID Format | Verify system rejects NID with incorrect format | 1. Navigate to voter login page 2. Enter an NID that is not 16 digits 3. Enter any DOB 4. Click 'Login' | NID: 12345 (too short) DOB: 1990-05-15 | Validation error displayed: 'Invalid NID format'. Form is not submitted. User remains on login page. | NID must be 10–13 digits with numbers only. | PASS | Acceptable
TC-03 | AUTH-F-1.0 (OVMS-23) | Voter Login — Wrong Credentials | Verify system shows error on incorrect NID/DOB combination | 1. Navigate to voter login page 2. Enter a valid-format NID that exists 3. Enter an incorrect DOB 4. Click 'Login' | NID: 1234567890123 Voter ID: VTR-2081-000001 Password: pwd1234567890123 | Error message: 'Invalid credentials'. Attempt counter increments. User remains on login page. | Same as expected | PASS | worked fine
TC-04 | AUTH-F-1.0 (OVMS-23) | Voter Login — Account Lockout after 5 Failed Attempts | Verify account is temporarily blocked after 5 consecutive failed login attempts | 1. Navigate to voter login page 2. Enter invalid credentials 5 times in succession 3. Attempt a 6th login | NID: 1234567890123456 DOB: (incorrect, repeated 5×) | After 5th failure, account is blocked. Error: 'Account temporarily locked. Please try again later.' 6th attempt is rejected immediately. | Account locked for 15 minutes after 5 failed attempts. | PASS | worked fine
TC-05 | AUTH-F-1.0 (OVMS-23) | Voter Login — HTTPS Enforcement | Verify login form only transmits credentials over HTTPS | 1. Open browser Developer Tools → Network tab 2. Submit a valid voter login 3. Inspect the request | NID: valid DOB: correct | Request URL uses https://. No credentials appear in plaintext in network logs. | Same as expected | PASS | worked fine
TC-06 | AUTH-F-2.0 (OVMS-34) | Admin Login — Valid Email, Password and OTP | Verify admin can log in with correct email, password and valid OTP | 1. Navigate to https://private.votingsystem.tech/admin/login 2. Enter registered admin email 3. Enter correct password 4. Click 'Send OTP' 5. Enter received OTP code 6. Click 'Verify' | Email: votingsystemadmin@ovms.com Password: password OTP: (from email) | Admin is redirected to Admin Dashboard. Two-factor verification is complete. Session is created with admin privileges. | As expected | PASS | worked fine
TC-07 | AUTH-F-2.0 (OVMS-34) | Admin Login — Expired OTP | Verify system rejects OTP that has expired | 1. Navigate to admin login 2. Enter valid credentials and request OTP 3. Wait for OTP to expire (typically 5 minutes) 4. Enter the expired OTP code | Email: votingsystemadmin@ovms.com Password: password OTP: expired otp | Error displayed: 'OTP has expired. Please request a new one.' Admin is not authenticated. | Incorrect or expired code. Please try again. | PASS | worked fine
TC-08 | AUTH-F-2.0 (OVMS-34) | Admin Login — Account Lock after 5 Failed Attempts | Verify admin account locks after 5 consecutive failed login attempts | 1. Navigate to admin login 2. Enter valid email but wrong password 5 times | Email: votingsystemadmin@ovms.com Password: Wrong@pass (5×) | After 5th failure, error: 'Account locked due to too many failed attempts.' Subsequent attempts are rejected. | Account locked. Try again in 15 mins. | PASS | Acceptable
TC-09 | AUTH-F-2.0 (OVMS-34) | Admin Session — Auto-Expiry after 30 Minutes Inactivity | Verify admin session expires automatically after 30 minutes of inactivity | 1. Log in to admin panel 2. Leave the session idle for 30+ minutes 3. Attempt to navigate to any admin page | Valid admin session Inactivity: 30+ minutes | Admin is redirected to the login page. Session cookie is invalidated. Error/info message: 'Your session has expired.' | As expected | PASS | Acceptable
TC-10 | VM-F-1.0 (OVMS-25) | Voter Dashboard — Displays Correct Active Pools | Verify voter dashboard only shows active election pools for voter's own constituency | 1. Log in as a voter with a known constituency 2. View the voter dashboard 3. Check pools displayed | Voter constituency: Kathmandu-1 Active pools: Pool A (Kathmandu-1), Pool B (Lalitpur-2) | Only Pool A is visible. Pool B (different constituency) is not shown. Dashboard correctly identifies voter's constituency. | As expected | PASS | worked fine
TC-11 | VM-F-1.0 (OVMS-25) | Voter Dashboard — Already-Voted Pool Hidden | Verify that pools in which the voter has already cast a vote are not displayed | 1. Cast a vote in Pool A as voter 2. Log out 3. Log back in 4. Check dashboard | Voter has voted in Pool A | Pool A is no longer displayed on the dashboard. Only remaining unvoted active pools are shown. | Vote now button is disabled | PASS | Acceptable
TC-12 | VM-F-2.0 (OVMS-24) | Session — Auto-Termination after 10 Minutes Inactivity | Verify voter session auto-terminates after 10 minutes of inactivity | 1. Log in as a voter 2. Leave the session idle for 10+ minutes 3. Attempt to interact with the dashboard | Valid voter session Inactivity: 10+ minutes | Voter is redirected to login page. Error/info: 'Session expired due to inactivity.' Voter must re-authenticate. | As expected | PASS | Acceptable
TC-13 | VM-F-2.0 (OVMS-24) | Access Restriction — Voter Cannot Vote Twice in Same Pool | Verify server-side enforcement prevents a voter from casting a second vote in the same pool | 1. Log in as voter and cast a vote in Pool A 2. Attempt to navigate directly to Pool A voting URL | Voter: already voted in Pool A Direct URL: /voter/vote/poolA | System detects vote already cast. Redirects to dashboard with message: 'You have already voted in this election.' Vote page is inaccessible. | cant be accessible | PASS | Acceptable
TC-14 | VT-F-1.0 (OVMS-29) | Identity Verification Modal — Valid Citizenship Number and CAPTCHA | Verify voter can pass identity verification with correct citizenship number and CAPTCHA | 1. Log in as voter 2. Click 'Vote Now' on an active pool card 3. Enter valid citizenship number in modal 4. Complete CAPTCHA 5. Click 'Verify' | Citizenship No: 12-34-567890 CAPTCHA: (complete correctly) | Identity verification passes. Voter is taken to the candidate selection/ballot screen. | Few digit of nid has been implemented as security verification and captcha isnt implemented. | PASS | Acceptable
TC-15 | VT-F-1.0 (OVMS-29) | Identity Verification — Wrong Citizenship Number | Verify system blocks entry when citizenship number does not match voter record | 1. Log in as voter 2. Click 'Vote Now' 3. Enter wrong nid digits 4. Click 'Verify' | Nid digits: 00-00-000000 (wrong) | Error displayed in modal: 'invalid.' Attempt counter increments. | As expected | PASS | Acceptable
TC-16 | VT-F-1.0 (OVMS-29) | Identity Verification — Lockout after 3 Failed Attempts | Verify voting is blocked after 3 failed identity verification attempts | 1. Log in as voter 2. Click 'Vote Now' 3. Enter wrong citizenship number 3 times | Citizenship No: (wrong × 3) | After 3rd failure, modal/page blocked. Error: 'Maximum verification attempts reached. Please contact admin.' Voter cannot proceed to ballot. | As expected | PASS | worked fine
TC-17 | VT-F-2.0 (OVMS-31) | Vote Confirmation Screen — Correct Candidate Displayed | Verify confirmation screen accurately displays the selected candidate's details | 1. Pass identity verification 2. Select a candidate from the ballot grid 3. Click 'Vote Now' 4. View confirmation screen | Selected candidate: Ram Bahadur (Nepali Congress, Pool A) | Confirmation screen shows: candidate full name, party name, party symbol, and pool name. Includes warning: 'This action cannot be undone.' 'Confirm Vote' button is visible. | As expected | PASS | worked fine
TC-18 | VT-F-2.0 (OVMS-31) | Vote Confirmation Screen — Cancel Returns to Ballot | Verify voter can cancel at confirmation screen and return to ballot without vote being cast | 1. Reach vote confirmation screen 2. Click 'Cancel' or 'Go Back' | No vote cast yet | Voter is returned to the candidate selection screen. No vote record is inserted into the database. | As expected | PASS | worked fine
TC-19 | VT-F-3.0 (OVMS-32) | Vote Submission — Successful Vote and Receipt Code | Verify vote is recorded in the database and a unique receipt code is displayed | 1. Complete identity verification 2. Select candidate 3. Confirm on confirmation screen 4. View post-vote screen | Voter: valid Candidate: selected Confirmation: clicked | Vote row inserted in votes table (voter_hash + pool_id + candidate_id). Unique receipt code displayed on screen. Auto-logout countdown of 5 seconds begins. | As expected | PASS | worked fine
TC-20 | VT-F-3.0 (OVMS-32) | Vote Submission — Auto-Logout after Receipt | Verify voter is automatically logged out 5 seconds after receipt is shown | 1. Complete full voting process 2. View receipt screen 3. Wait 5 seconds without interaction | Successful vote cast | After 5-second countdown, voter session is destroyed and browser redirects to the voter login page. | As expected | PASS | worked fine
TC-21 | VT-F-3.0 (OVMS-32) | Vote Submission — Atomicity (No Partial Vote) | Verify vote is not partially recorded if session drops mid-submission | 1. Start vote submission 2. Simulate network interruption during POST request 3. Check database | Network drop simulated via browser DevTools (offline mode) mid-submission | Either vote is fully recorded (with receipt) OR not recorded at all. No partial/duplicate vote exists in the votes table. | As expected | PASS | worked fine
TC-22 | CM-F-1.0 (OVMS-26) | Candidate List — Filter by District and Constituency | Verify admin can filter candidate listings by district and constituency | 1. Log in as admin 2. Navigate to Candidate Management 3. Select a district from the filter dropdown 4. Select a constituency 5. View results | District: Bagmati Constituency: Kathmandu-1 | Only candidates registered for Kathmandu-1 constituency are displayed. Candidate cards show name, party, and nomination status. | As expected | PASS | worked fine
TC-23 | CM-F-2.0 (OVMS-40) | Add Candidate — Auto-Fill via NID Lookup | Verify citizen details auto-populate when admin enters a valid NID on the add-candidate form | 1. Log in as admin 2. Navigate to Add Candidate 3. Enter a valid NID in the NID field 4. Observe form fields | NID: 1234567890123456 (existing citizen) | Citizen's full name, date of birth, address, and constituency auto-populate from the citizens table. Party symbol auto-loads on party selection. | As expected | PASS | worked fine
TC-24 | CM-F-2.0 (OVMS-40) | Add Candidate — NID Not Found | Verify system shows error when NID does not exist in the citizens table | 1. Log in as admin 2. Navigate to Add Candidate 3. Enter a non-existent NID | NID: 9999999999999999 (not in DB) | Error displayed: 'NID not found in citizen registry.' Form fields remain empty. Admin cannot proceed without a valid NID. | As expected | PASS | worked fine
TC-25 | CM-F-2.0 (OVMS-40) | Edit Candidate — Update Active/Inactive Status | Verify admin can change candidate nomination status and change is persisted | 1. Log in as admin 2. Navigate to Candidate Management 3. Click Edit on a candidate 4. Change status to 'Inactive' 5. Save | Candidate status: Active → Inactive | Candidate status is updated in the database. Candidate list reflects new status immediately. Inactive candidates do not appear on voter ballot. | As expected | PASS | worked fine
TC-26 | PM-F-1.0 (OVMS-42) | Pool List — View and Filter Election Pools | Verify admin can view all pools and filter by constituency or election type | 1. Log in as admin 2. Navigate to Pool Management 3. Apply filter: constituency = 'Kathmandu-1' | Pools in DB for different constituencies | Table shows pool name, type, and status. Filtered results show only Kathmandu-1 pools. Status labels (upcoming/active/closed) are visually distinguishable. | As expected | PASS | worked fine
TC-27 | PM-F-2.0 (OVMS-43) | Create Pool — Valid Pool with Future End Date | Verify admin can successfully create a new election pool | 1. Log in as admin 2. Navigate to Create Pool 3. Enter pool name, type, constituency 4. Set start date to today, end date to next week 5. Submit | Pool Name: General Election 2026 Type: National Constituency: Kathmandu-1 Start: today End: 7 days later | Pool created and appears in pool list with status 'Upcoming'. Database record inserted correctly with all fields. | As expected | PASS | worked fine
TC-28 | PM-F-2.0 (OVMS-43) | Create Pool — End Date Before Start Date Rejected | Verify system validates that end date must be after start date | 1. Log in as admin 2. Navigate to Create Pool 3. Set end date earlier than start date 4. Submit | Start: 2026-05-01 End: 2026-04-01 (before start) | Validation error: 'End date must be later than start date.' Pool is not created. Form remains with error highlighted. | As expected | PASS | worked fine
TC-29 | AM-F-1.0 (OVMS-37) | Admin Dashboard — Real-Time Metrics Display | Verify admin dashboard shows dynamically updated counts for voters, candidates, and votes cast | 1. Log in as admin 2. View Admin Dashboard 3. Cast a new test vote in a separate browser 4. Reload dashboard metrics | Pre-test: known vote counts in DB | Dashboard shows total voters, total candidates, total votes cast. After new vote is cast, metric updates on reload without full page rebuild. | As expected | PASS | worked fine
TC-30 | AM-F-1.1 (OVMS-38) | Admin Audit Log — Action Recorded with Timestamp and IP | Verify administrative actions are logged with timestamp and IP address | 1. Log in as admin 2. Perform an action (e.g., add a candidate) 3. Navigate to Audit Log | Admin action: Add Candidate (NID: 1234567890123456) | New entry appears in audit log with: action description, timestamp (correct date/time), admin's IP address. Entry persisted in database. | As expected | PASS | worked fine
TC-31 | AM-F-2.0 (OVMS-35) | Admin Profile — Change Password with Correct Current Password | Verify admin can successfully change their password | 1. Log in as admin 2. Navigate to Profile → Change Password 3. Enter current password 4. Enter new password and confirm 5. Submit | Current: Admin@1234 New: NewAdmin@5678 Confirm: NewAdmin@5678 | Password updated successfully. Confirmation message shown. Admin can log in with new password on next session. | As expected | PASS | worked fine
TC-32 | AM-F-2.0 (OVMS-35) | Admin Profile — Password Change Fails with Wrong Current Password | Verify system rejects password change if current password is incorrect | 1. Log in as admin 2. Navigate to Profile → Change Password 3. Enter wrong current password 4. Submit | Current: WrongPassword New: NewAdmin@5678 | Error: 'Current password is incorrect.' Password is not changed. Admin remains on the change password page. | As expected | PASS | worked fine
TC-33 | UM-F-1.0 (OVMS-39) | Voter Search — Find by Full NID | Verify admin can search for a voter using their exact NID | 1. Log in as admin 2. Navigate to User Management / Voter Search 3. Enter full NID 4. Click Search | NID: 1234567890123456 (exists in DB) | Voter record displayed: full name, NID, DOB, address, constituency, and linked citizen record details. | As expected | PASS | worked fine
TC-34 | UM-F-1.0 (OVMS-39) | Voter Search — Partial Name Search | Verify admin can find voters using a partial name entry | 1. Log in as admin 2. Navigate to User Management 3. Enter partial name 'Ram' in the search field | Search term: 'Ram' | All voters with 'Ram' in their name are returned. Results show name, NID, and constituency. Non-matching records are not shown. | As expected | PASS | worked fine
TC-35 | UM-F-1.0 (OVMS-39) | Voter Search — Non-Admin Access Blocked | Verify voter accounts cannot access the voter search / user management panel | 1. Log in as a regular voter 2. Attempt to navigate directly to /admin/users | Voter session (non-admin) | Access denied. Voter is redirected to voter dashboard or login page with error: 'Unauthorised access.' | As expected | PASS | worked fine
TC-36 | RM-F-1.0 (OVMS-46) | Results Portal — Publicly Accessible Without Login | Verify that the results portal can be accessed by any user without authentication | 1. Open a browser in incognito mode (no session) 2. Navigate to http://[BASE_URL]/results | No session / no login | Results page loads successfully. Live vote counts per candidate are visible. No login prompt is shown. | As expected | PASS | worked fine
TC-37 | RM-F-1.0 (OVMS-46) | Results Portal — Filter by Area and Pool | Verify results can be filtered by constituency area and specific election pool | 1. Navigate to results portal 2. Select area: 'Kathmandu' 3. Select pool: 'General Election Pool A' | Multiple pools and areas in DB | Results filtered to show only candidates and vote counts for the selected pool in Kathmandu. Other pool results hidden. | As expected | PASS | worked fine
TC-38 | RM-F-1.0 (OVMS-46) | Results Portal — Near-Real-Time Update | Verify results update to reflect newly cast votes without a full page reload | 1. Open results portal 2. Cast a vote in another browser tab/session 3. Observe results page | Vote cast for Candidate A in Pool A | Candidate A's vote count on the results portal increases without requiring a manual page refresh (within the polling interval). | As expected | PASS | worked fine
TC-39 | SYS-F-1.0 (OVMS-56) | NID Validation — Correct Format Accepted | Verify system accepts NID with exactly 16 numeric digits and proceeds with DB lookup | 1. Enter a 16-digit numeric NID on voter login 2. Submit | NID: 1234567890123456 | NID format validation passes. System queries the citizens table. Result (found/not found) returned correctly. | As expected | PASS | worked fine
TC-40 | SYS-F-1.0 (OVMS-56) | NID Validation — Invalid Format Blocked Before DB Query | Verify system rejects malformed NID before querying the database | 1. Enter NID with letters or wrong length 2. Submit | NID: ABCD12345 (invalid) NID: 123 (too short) | Client/server-side validation triggers. Error: 'Invalid NID format.' No database query is executed. | As expected | PASS | worked fine
TC-41 | SYS-F-2.0 (OVMS-57) | Constituency Auto-Sync — Voter NID Mapped to Correct Constituency | Verify the system auto-assigns constituency based on voter's NID permanent address | 1. Register/use a voter with a known NID address (Kathmandu) 2. Log in as that voter 3. Observe assigned constituency on dashboard | Voter NID address: Kathmandu district permanent address | Dashboard shows constituency as 'Kathmandu-1' (or correct mapped constituency). Only pools for that constituency are displayed. | As expected | PASS | worked fine
TC-42 | SYS-ENV-1.0 (OVMS-61) | Live Hosting — Application Loads via domain | Verify the application is accessible via the Azure VM public URL | 1. Open a browser on a machine outside the Azure VM 2. Navigate to https://votingsystem.tech | URL: https://votingsystem.tech | Application homepage/login loads correctly. No server errors. Web server (Apache/Nginx) is running on Ubuntu. | As expected | PASS | worked fine
TC-43 | SYS-DB-1.0 (OVMS-2) | Database Integrity — Foreign Key Constraints Enforced | Verify that deleting a referenced record (e.g., a pool) does not silently break the votes table | 1. Log in as admin 2. Attempt to delete a pool that has existing vote records | Pool A has 5 votes recorded | System prevents deletion with error: 'Cannot delete pool with existing votes.' OR cascades deletion correctly per schema design. No orphan records exist. | As expected | PASS | worked fine
TC-44 | SYS-DEV-1.0 (OVMS-59) | GitHub Repository — Branching Strategy Verified | Verify main and dev branches exist and sensitive credentials are excluded from version control | 1. Navigate to the GitHub/GitLab repository 2. Check branches 3. Review committed files for credentials | GitHub repo URL: https://github.com/Awwdrsh/Online-Voting-System-and-Management# | main' and 'dev' branches exist. No .env files, database passwords, or API keys present in any committed files. .gitignore includes credential files. | As expected | PASS | worked fine
TC-45 | SYS-UX-1.0 (OVMS-53) | Wireframes / Figma — Voter Dashboard Mockup Matches Implementation | Verify the implemented voter dashboard UI matches the approved Figma wireframes | 1. Open approved Figma mockup for voter dashboard 2. Open the live voter dashboard 3. Compare layout, components, and navigation | Figma mockup: Voter Dashboard (approved) Live URL: https://votingsystem.tech/ovms/voter/dashboard | Layout, pool cards, navigation sidebar, and typography match the approved wireframe within agreed tolerance. No major UI deviations. | Some changes have been observed | PASS | Acceptable
TC-46 | OVMS-64 | Voter Session | Verify single-session enforcement | 1. Log in as Voter on Browser A. 2. Log in as same Voter on Browser B. 3. Attempt to navigate on Browser A. | Valid Voter Credentials | Browser A session is terminated immediately. Browser A redirects to login with message: "Session expired or logged in from another device." | As expected | PASS | Acceptable
TC-47 | OVMS-64 | Voter Session | Verify 10-minute inactivity timeout | 1. Log in as Voter. 2. Leave browser idle for 11 minutes. 3. Click any dashboard link. | Valid Voter Session | User is redirected to login page. Session token is destroyed server-side. | As expected | PASS | Acceptable
TC-48 | OVMS-63 | Admin Login | Verify login requires CAPTCHA & Email OTP | 1. Navigate to Admin Login. 2. Enter credentials & solve CAPTCHA. 3. Enter OTP from email. | Admin Email/Pass, Valid CAPTCHA, Valid OTP | Admin is successfully logged in only after both CAPTCHA and OTP validations pass. | As expected | PASS | Acceptable
TC-49 | OVMS-66 | App Security | Verify XSS & SQLi mitigations | 1. Navigate to Admin Search. 2. Enter <script>alert('XSS')</script> 3. Enter ' OR 1=1-- | XSS & SQLi payloads | Input is sanitized. Scripts do not execute. Database does not return unauthorized records. | As expected | PASS | Acceptable
TC-50 | OVMS-65 | Voter UI | Verify Interactive Guide and Breadcrumbs | 1. Log in to Voter Portal. 2. Locate "How to Vote" guide. 3. Navigate deep into profile and check breadcrumbs. | N/A | Guide is visible and dismissible. Breadcrumbs accurately reflect the navigation path. | As expected | PASS | Acceptable
TC-51 | OVMS-85 | Infra Security | Verify Admin/Security Portals require VPN | 1. Disconnect from corporate VPN. 2. Attempt to access /admin or /security URLs. | Public IP address | Server returns 403 Forbidden or 404 Not Found. Portal does not load. | As expected | PASS | Acceptable
TC-52 | OVMS-67 | Infra Security | Verify sensitive files are isolated | 1. Navigate directly to http://[BASE_URL]/.env 2. Navigate to /vendor | Direct URLs to configs | Server returns 403 Forbidden or 404 Not Found. File contents are not disclosed. | As expected | PASS | Acceptable
TC-53 | OVMS-75 | Results UI | Verify Results Portal matches Wireframes | 1. Navigate to Results Portal. 2. Compare CSS, charts, and layout to Figma wireframes. | Live Results | UI aligns perfectly with designs. Charts render correctly and layout is mobile-responsive. | As expected | PASS | Acceptable
TC-54 | OVMS-68 | Transport Sec | Verify SSL/TLS and Secure Headers | 1. Navigate to http://[BASE_URL]. 2. Inspect Network headers. | N/A | Auto-redirects to https://. Response includes Strict-Transport-Security (HSTS) and Content-Security-Policy (CSP) headers. | As expected | PASS | Acceptable
TC-55 | OVMS-76 | Monitoring | Verify Wazuh agent alerts on file changes | 1. SSH into server. 2. Modify a tracked config file (e.g., nginx.conf). 3. Check Wazuh dashboard. | Modified file | Wazuh triggers a File Integrity Monitoring (FIM) alert within the specified interval. | As expected | PASS | Acceptable
TC-56 | OVMS-73 | Admin/Bugs | Verify Voter Deletion handles FK constraints | 1. Admin navigates to Voter Management. 2. Attempt to delete a voter who has already cast a vote. | Voter with existing vote | System handles constraint gracefully. Displays error "Cannot delete voter with active voting history" instead of crashing. | As expected | PASS | Acceptable
TC-57 | OVMS-72 | Admin/Bugs | Verify Candidate Deletion handles FK constraints | 1. Admin navigates to Candidate Management. 2. Attempt to delete an active candidate linked to a pool. | Active Candidate | System prevents deletion and shows error, or safely archives candidate without SQL crash. | As expected | PASS | Acceptable
TC-58 | OVMS-74 | Admin UI | Verify Search & Filter on Data Tables | 1. Go to Admin Data Tables (e.g., Users). 2. Type in Search bar. 3. Apply a dropdown filter. | Search term: "Ram", Filter: "Active" | Table updates dynamically to show only rows matching the search term and applied filters. | As expected | PASS | Acceptable
TC-59 | OVMS-77 | Admin UI | Verify Admin Navigation Duplication is fixed | 1. Log in as Admin. 2. Inspect Top Bar and Left Nav Pane. | N/A | Main menu links are only in the Left Pane. Top bar only contains profile/logout. No duplicates. | As expected | PASS | Acceptable
TC-60 | OVMS-78 | Voter UI | Verify voted pools become inactive/grayed out | 1. Voter casts a vote in Pool A. 2. Return to Dashboard. 3. Attempt to click Pool A again. | Voted Pool | Pool A card is grayed out, shows "Voted" badge, and is unclickable. | As expected | PASS | Acceptable
TC-61 | OVMS-79 | Voter UI | Verify Voter Profile navigation visibility | 1. Log in as Voter. 2. Navigate to Profile page. 3. Check for sub-menus (Settings, History). | N/A | Navigation contents within the profile are fully visible and clickable without UI clipping. | As expected | PASS | Acceptable
TC-62 | OVMS-80 | Voting Flow | Verify Secondary Verification isn't bypassed | 1. Click "Vote Now" on a pool. 2. Attempt to manually change URL to skip verification modal. | Direct Ballot URL | System blocks access and forces user back to the Secondary Verification (OTP/Captcha) step. | As expected | PASS | Acceptable
TC-63 | OVMS-81 | Voting Flow | Verify Ballot/Summary UI matches wireframes | 1. Enter Ballot Screen. 2. Select candidate. 3. View Summary screen. | Valid Vote Flow | Candidate cards, party logos, and confirmation summary layout exactly match Figma designs. | As expected | PASS | Acceptable
TC-64 | OVMS-83 | Admin UI | Verify Admin Dashboard layout proportions | 1. Log in as Admin. 2. View Dashboard KPI cards and charts. | N/A | Layout is proportional. Elements do not overlap on standard desktop resolutions (1080p). | As expected | PASS | Acceptable
TC-65 | OVMS-84 | Auth Security | Verify Voter Login OTP cannot be bypassed | 1. Enter NID/DOB. 2. Intercept API request or manually edit URL to jump to /dashboard. | Valid NID/DOB | Access denied. Server requires verified OTP token before granting dashboard access. | As expected | PASS | Acceptable
TC-66 | OVMS-86 | Info Sec | Verify Fuzz testing configs are blocked | 1. Run dirb/gobuster against webroot looking for .git, config.php.bak. | Fuzzing Wordlist | Server blocks all requests to hidden/backup files with 403 Forbidden. | As expected | PASS | Acceptable
TC-67 | OVMS-87 | Core Logic | Verify PR Ballot shows Parties, not Candidates | 1. Log in as Voter. 2. Enter a Proportional Representation (PR) pool ballot. | PR Pool | Ballot displays registered Political Parties and their symbols. Individual candidate names are NOT shown. | As expected | PASS | Acceptable
Test Modules | Test Case ID | Remarks
Authentication & Authorization | TC-01 to TC-09, TC-48, TC-65 | 11 Passed
Voter Dashboard & Session Management | TC-10 to TC-13, TC-46, TC-47, TC-50, TC-60, TC-61 | 9 Passed
Voting Process & Ballot | TC-14 to TC-21, TC-62, TC-63, TC-67 | 11 Passed
Admin, Candidate & Pool Management | TC-22 to TC-35, TC-56, TC-57, TC-58, TC-59, TC-64 | 19 Passed
Results Portal | TC-36 to TC-38, TC-53 | 4 Passed
Infrastructure, System & Security | TC-39 to TC-45, TC-49, TC-51, TC-52, TC-54, TC-55, TC-66 | 13 Passed